## Sample
Company Logo Here |  | Construction Company Name Street Address City, County, Post Code 0110 1111111 address@email.co.uk constructioncompanyweb+site.com
Sample Construction Schedule
Project Name |  | 49 Vine Street
Stage |  | Tasks | Duration (Days) | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month
|  |  |  | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
| Pre-Construction |  | 63
|  | Contracts | 31
|  | Property Agreements | 31
|  | Floor Plans | 14
|  | Financing | 14
|  | Document Review & Revisions | 7
|  | Document Approval | 7
|  | Bids | 7
|  | Surveying | 31
|  | Permitting | 31
| Construction: Foundation |  | 30
|  | Site Work | 7
|  | Excavation | 2
|  | Foundation | 20
|  | Foundation Inspection | 1
| Construction: Framing, Floor, Walls, and Roof |  | 35
|  | Set Steel | 2
|  | Wall Framing | 3
|  | Roof Framing | 11
|  | Window & Door Installation | 2
| Construction: Electrical, Plumbing |  | 42
|  | Plumbing | 30
|  | Electrics | 20
| Construction: Exterior Finishes |  | 27
|  | Roofing | 3
|  | Brickwork | 4
|  | Walkaways and Driveway Pour | 20
| Construction: Interior Walls, Insulation, Trim & Tile |  | 80
|  | Interior Walls | 30
|  | Tile Installation | 45
|  | Exterior Painting | 45
| Construction: Interior Finishes, Paint & Flooring |  | 22
|  | Interior Door Installation | 1
|  | Cabinetry Installation | 1
|  | Flooring Installation | 3
|  | Interior Painting | 14
| Fixtures, Appliances, Etc. |  | 20
|  | Appliance Installation | 2
|  | Doors | 3
|  | Bathroom | 5
|  | Shower Doors | 3
|  | Mirrors | 1
| Final Walk Through & Cleaning |  | 22
|  | Final Walk Through | 3
|  | Paint Touch Ups | 5
|  | Final Clean | 5
| Exterior Landscaping |  | 34
|  | Patios/ Porches/ Decks/ Fencing/ Front Gate | 14
|  | Driveway | 7
| Final Walk-Through |  | 3
|  | Final Walk-Through | 2
|  | Move In | 1